Section 8: Particular Conditions of Contract

The following Particular Conditions of Contract shall supplement the GCC. Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| A. General |  |
| --- | --- |
| GCC 1.1 (d) | The financing institutions is: Asian Development Bank (ADB) |
| GCC 1.1 (r) | The Employer is: Project Management Unit (PMU), Enhancing Climate Resilience and Food Security Project, Ministry of Tourism and Environment (MOTE) |
| GCC 1.1 (w) | The Intended Completion Date for the whole of the Works shall be 18 months from the Start Date |
| GCC 1.1 (cc) | The Project Manager is: To be named later |
| GCC 1.1 (ff) | The new HAC multipurpose facility will be constructed at the current HAC premises in Hanimaadhoo. The HAC is located on the eastern side of Hanimaadhoo island, occupying a plot assigned by the local island council. The new HAC multipurpose facility will be constructed on the northern side of the current plot (see drawings, Figure 3). |
| GCC 1.1 (ii) | The Start Date shall be: 28 days after the signing the contract |
| GCC 1.1 (mm) | The Works consist of: Design and construction of the HAC multipurpose facility composed of two separate buildings - an office building and a laboratory building, with a distance of 10m between the two buildings. The office building will have a total of three floors, consisting of a ground floor, first floor and second floor. The laboratory building will have two floors, consisting of a ground floor and first floor. |
| GCC 2.2 | Sectional Completions are: Not Applicable |
| GCC 2.3 (j) | The following documents also form part of the Contract: - Initial Environmental Assessment - Gender Assessment and Action Plan - Due Diligence Report Output 3 |
| GCC 3.1 | The language of the contract is: English The law that applies to the Contract is the law of: Republic of Maldives |
| GCC 11.1 | The Project Manager may delegate any of his duties and responsibilities. |
| GCC 14.1 | Schedule of other contractors: Not Applicable |
| GCC 19.1 | The minimum insurance amounts and deductibles shall be: (a) for loss or damage to the Works, Plant and Materials: 1.1 times Accepted Contract Amount (b) for loss or damage to Equipment: 1.1 times the cost of Equipment (c) for loss or damage to property (except the Works, Plant, Materials, and Equipment) in connection with Contract: USD 250,000 (d) for personal injury or death: - of the Contractor’s employees: As per applicable law - of other people: USD 60,000 |
| GCC 20.1 | Site Investigation Reports are: Not Applicable |
| GCC 21.2 | Protection of the Environment The Contractor shall comply with all applicable national and island environmental provisions, laws and regulations. The Contractor shall also comply with all reasonable requests of the national and local authorities responsible for enforcing environmental controls. Within 28 days of the Commencement Date and prior to field mobilization the Contractor shall submit a detailed Site Specific Environmental Management Plan (SSEMP) including OHS Plan, based on the Environment, Health and Safety (EHS) Management Plan submitted in the technical proposal, for the Project Manager’s no objection showing how the Contractor intends to comply with environmental laws and regulations and other specific requirements prescribed in the Contract, addressing all the monitoring and mitigation measures set forth in the Environmental Impact Assessment (“EIA”)/Initial Environmental Examination (IEE), as applicable, and the Environmental Management Plan (“EMP”) of the project attached in Section 6- Employer’s Requirements. Work shall not commence on the Site until the no objection of SSEMP has been obtained from the Project Manager and is being implemented along with mobilization of fulltime environmental safeguards, and health & safety staff with subject-matter expertise. The Contractor shall (a) establish an operational system for managing environmental and health and safety impacts, (b) comply with the approved SSEMP and OHS Plan, and any corrective or preventative actions set out in safeguards monitoring reports that the Employer will prepare from time to time to monitor the implementation of the project EMP through the SSEMP and OHS Plan, (c) allocate sufficient budget required to ensure that such measures, requirements and actions are carried out, (d) submit monthly reports on the compliance of such measures to the Employer. Where unanticipated environmental risks or impacts become apparent during the Contract, the Contractor is required to update the SSEMP and OHS Plan to outline the potential impacts to site works and associated mitigation measures for the Project Manager’s approval.” |
| GCC 23.1 | The following shall be designed by the Contractor: Complete HAC multipurpose facility comprising of two separate buildings - an office building and a laboratory building, with a distance of 10m between the two buildings. The office building will have a total of three floors, consisting of a ground floor, first floor and second floor. The laboratory building will have two floors, consisting of a ground floor and first floor. |
| GCC 24.2 | The Contractor is responsible for establishment of preventive and emergency preparedness and response measures to avoid, and where avoidance is not possible, to minimize adverse impacts and work site health and safety risks to workers and local communities. Within 28 days of signing the contract the Contractor shall submit a detailed Site Specific Environmental Management Plan (SEMP) and Occupational Health and Safety Plan (OHS), based on the Environmental Health and Safety Management Plan submitted by the contractor in their technical proposal seeking Project Manager’s no objection. The SEMP shall include emergency protocol, traffic management plan, labor camp standards, material stockpile and hazardous material storage area, and worker’s code of conduct. The Contractor shall comply with the local Health and Safety laws and regulations as prescribed in the Contract, taking into account the Supplementary Information in Section 6- Employer’s Requirements. Work shall not commence on the Site until the confirmation of no objection to the SEMP and OHS Plan has been obtained from the Project Manager and environment, and health and safety staff (CVs approved by the Engineer)are mobilized. Where unanticipated health and safety hazards or risks become apparent during the work, the Contractor is required to update the SEMP and OHS Plan to outline the potential impacts and associated mitigation measures for the Project Manager’s no objection. The Contractor shall comply with the approved SEMP and OHS Plan and any corrective or preventative actions that the Employer instructs or will prepare from time to time to monitor the implementation of the approved SSEMP and OHS Plan. Contractor shall provide formal appointment to all workers, personal identification card, account number for digital payment of wage, health-check record, and induction orientation. In particular, the Contractor is required to provide all personnel including Employer’s Personnel and visitors on site with personal protective equipment, including protection for feet (safety boots), head, eyes, ears (safety helmets) and hands, etc., in accordance with the Contractor’s OHS Plan. The Contractor should ensure that his Subcontractors also fully comply with the SEMP and OHS requirements and provide all such necessary equipment to their personnel. Although, the contractor will be fully liable to ensure full compliance with the environmental safeguards and safety requirements in the project irrespective of work being carried out by subcontractor. The Contractor shall bear full costs to ensure that such measures, requirements and actions are carried out, as instructed by the Engineer time to time. The Contractor shall submit monthly safeguards reports on the compliance of such measures to the Employer. In the event of injury involving medical treatment or hospitalization and fatal accident the Contractor shall immediately notify the Project Manager within 24 hours as preliminary incidence report and submit a formal report as soon as practicable after completing investigation and acquiring police report. For all accidents, whether fatal or not, the Contractor shall also notify the appropriate local authorities in accordance with the Laws of the Country. |
| GCC 26.1 | The Site Possession Date(s) shall be: 7 (seven) days after the signing of contract |
| GCC 29.1 | Appointing Authority for the Adjudicator: Ministry of Finance and Planning |
| GCC 30.3 | The Adjudicator shall be paid by the hour at the rate of: USD 40 per hour (not exceeding 8 hours per day) The reimbursable expenses are: Traveling expenses (only) |
| GCC 30.4 | Institution whose arbitration procedures shall be used: [select from below] (a) Contracts with foreign contractors: International arbitration shall be conducted in accordance with the rules of International Chamber of Commerce (ICC). Arbitration shall be administered by International Chamber of Commerce (ICC). The place of arbitration shall be: the place of the institution administering the arbitration. (b) Contracts with domestic contractors: Arbitration shall be conducted in accordance with the laws of the Employer's country. |
| GCC 34.2 | The following sentence shall apply: Respectful Work Environment The Contractor shall conduct training programs for its employees and Sub-contractors to raise awareness to observe the highest ethical standards and refrain from any form of bullying, discrimination, misconduct and harassment, including sexual harassment and shall, at all times, behave in a manner that creates an environment free of unethical behavior, and promotes a respectful work environment. The Contractor shall take appropriate action against any employees or Subcontractors, including suspension or termination of employment or sub-contract, if any form of unethical or inappropriate behavior is identified. The contractor and their workers shall fully abide at times with the ADB requirements to refrain from sexual exploitation, abuse and harassment (SEAH). The Contractor shall keep an up to date record of its employees and Subcontractors who have attended and completed such training programs and provide such records to the Employer or the Engineer at their first written request. They shall also organize refresher orientations time to time. |

| C. Time Control |  |
| --- | --- |
| GCC 35.1 | The Contractor shall submit for approval a Program for the Works within 14 (fourteen) days from the date of the Letter of Acceptance. |
| GCC 35.3 | The period between Program updates is 45 (forty-five) days. The amount to be withheld for late submission of an updated Program is USD 500 per day |

| D. Quality Control |  |
| --- | --- |
| GCC 43.1 | The Defects Liability Period is: 365 days. |

| E. Cost Control |  |
| --- | --- |
| GCC 53.1 | The currency of the Employer’s country is: Maldivian Rufiyaa |
| GCC 54.1 | The Contract is not subject to price adjustment in accordance with GCC Clause 54. |
| GCC 55.1 | The proportion of payments retained is: 5 (five) % |
| GCC 56.1 | The liquidated damages for the whole of the Works are 0.5% (0.005) per day. The maximum amount of liquidated damages for the whole of the Works is 15% of the final Contract Price. |
| GCC 57.1 | The Bonus for the whole of the Works is: Nil. The maximum amount of Bonus for the whole of the Works is: Nil. |
| GCC 58.1 | The Advance Payments shall be 10% of the Accepted Contract Amount, and shall be paid to the Contractor no later than 28 days of the receipt by the Employer of an acceptable unconditional bank guarantee. |
| GCC 58.3 | Repayment of the Advance Payments shall be: at a rate of 15% from each payment certificate. |
| GCC 59.1 | The Performance Security amount is: 10% of the Contract Price |

| G. Finishing the Contract |  |
| --- | --- |
| GCC 69.1 | Add the following at the end of the Sub-clause 69.1 “The Employer’s approval of the operating and maintenance manuals and the as built drawings shall be the pre-requisite for the Project Manager to issue a certificate of completion of the works.” |
| GCC 72.1 | The date by which operating and maintenance manuals are required is: no later than 28 days before the Contractor’s request to the Project Manager for issuance of the Completion certificate for the Works under GCC 69.1 The date by which “as built” drawings are required is: no later the 28 days before the Contractor’s request to the Project Manager for issuance of the Completion certificate for the Works under GCC 69.1 |
| GCC 72.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required in GCC 72.1 is: USD 100,000 |
| GCC 73.2 (h) | The maximum number of days is: 200 days |
| GCC 75.1 | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is: 25% |